| Committee Name | SmartGrowth Research Working Group |
| --- | --- |
| Committee Meeting Date♣ | 30 August 2012 |
| Author (s) | Steve Hill, Group Manager Customer Services Western BOP District Council |

# Facilitating the development of Maori Land – an update for the Smartgrowth Review

## Background

- The existing strategy has a number of actions listed under the heading of “facilitating the development of Maori Land.”

  - Undertaking a study to understand the current barriers to the development of housing on multiple owned Maori lands and to identify local collaborative solutions that would address these barriers. This is also to include Maori land held under Te Ture Whenua Act title.

  - Undertaking a pilot project for an Iwi/Hapu/Trusts/Individual Maori land titles, to develop Maori Land for housing and economic purposes.

  - Developing, in parallel with the pilot project, a toolkit of the key steps in the process of developing Maori Land with the intention that it can be utilised by Iwi/Hapu and replicated across the sub-region.

- Including within the toolkit a Tangata Whenua management plan methodology/template which can be used as a base method for planning by Tangata Whenua to meet their protection and development aspirations.

  - (i)	Undertake an assessment on the 12 identified areas to determine feasibility of future pilot projects.

- (ii)	If feasible, then Iwi/Hapu/Trusts can plan for the development of their own lands, actively supported by the Councils, by utilising the toolkit and learnings from the pilot project.

- (iii)	Investigation (by MLC) regarding methods to aggregate land (as opposed to amalgamation) to facilitate utilisation of Maori Land.

  - Encouraging the promotion of common objectives for land development between Trusts and beneficial owners.

  - Examine and clarify funding sources for the undertaking of iwi and hapu management plans.

  - Examine, develop and advocate for funding sources and provision of capital (including considering underwriting and guarantor arrangements) that would assist with the development of Maori Land.

## Actions to date

- The Report Card

- The report card identified the following actions:

| - Actions that have been achieved |  |
| --- | --- |
| - Facilitation of Development of Maori Land | - Policy implemented in Regional Policy Statement to support development of multiple-owned Maori Land. - Te Keteparaha Mo Nga Papakainga – Maori Housing Toolkit completed to facilitate development of housing multiple-owned Maori land. - Training programme developed to promote common objectives for land development between Maori Land Trusts with Tauranga Moana Maori Trust Board, Western Bay of Plenty Housing Forum and Joint Agency Group. More than 50 Trusts have attended the workshops and training programme. - A Community Development and structure plan has been prepared for Maketu. |
| - Actions that have been significantly progressed |  |
| - Facilitation of Development of Maori Land | - Research to develop and advocate for funding sources and capital provision (including considering underwriting and guarantor arrangements) for development of Maori land was undertaken by the Maori Trust Board and others – Te Kahika Pilot project, Horoparaikete and Mangatawa. - A Community Plan has been prepared for Te Puna in consultation with tangata whenua and Maori landowners to identify future land use aspirations and determine whether any changes to relevant plans and strategies or structure planning will be required. Pirirakau hapu has signalled a review of their Hapu Management Plan in 2012. This will inform the Te Puna Community Plan. |
| - Actions that have not been achieved or significantly progressed |  |
| - Facilitation of Development of Maori Land | - Providing support and recognition of Maori Housing Forum as leaders in implementation of this action. - Investigation methods to aggregate land rather than amalgamate Maori land. - Gain a better understanding of iwi/hapu level demographic forecasts and trends in the sub-region. |

- In addition the Report Card Summary identifies that “On-going resources (are) required to support the facilitation of housing development on Maori land through implementation of the Papakainga toolkit”.

## Update

- Within this review period significant experience has been gained on the subject of facilitating the development of housing on Maori land.  The toolkit that has been completed has been written in such a way as to be proof to the variances and vagaries around legislative and organisational change over time so that the toolkit remains credible and valid.   The toolkit is applicable across the full continuum of preparedness, from owners that have not yet formed Trusts through to Trusts that are substantially ready to develop.   The toolkit has been used to assess progress across the continuum and has supported decision-making for funding applications by Trusts within the sub-region in a collaborative and non-competitive manner.   The toolkit has received national recognition as a valuable and credible resource and has been made freely available through the internet.

Workshops have been held with trusts throughout 2011 using the Toolkit as the structure for the learnings.  These workshops have been supported by the Joint Agencies and the Western Bay of Plenty Maori Housing Forum.  Trusts that completed the Workshops are being supported to progress their developments.  All trusts have progressed including two Trusts that have been successful with funding applications for houses with the Department of Building & Housing from leftover funds in the 2011/2012 Financial Year.   It has been the nationally recognised success of this sub-regional approach, and the valuable people and experience available to this sub-region that resulted in the Department seeking applications from the sub-region at short notice for funding.  Again it is due to the afore-mentioned factors that two applications were made, and two applications were successful.

- Workshops are in progress with new participants in the 2012 calendar year and as has been mentioned previously, this includes supporting Trusts that have completed earlier workshops.  Another measure of success that has been achieved is that where appropriate, Trusts are not only considering land owned individually by the Trust, they are looking holistically at blocks of adjoining land held by other Trusts for better development outcomes.  The workshop process has provided the opportunity and non-threatening environment where these important outcomes can be considered.

## Challenges that remain to be addressed

- Positive and nationally recognised momentum has been built up from the successes to-date.  Maintaining this momentum is the most significant challenge and relies on:

- Retaining the expertise that has been generated by the sub-region within the sub-region.  There is no doubt that a large measure of the success so far has been because of the people that have been available to the sub-region.  Most have been provided by the Joint Agencies as part of their commitments, but a critical position, that of Project Manager has been provided through a consultancy arrangement.  Funding for that arrangement has not been committed moving forward.

- The current Smartgrowth Strategy has little provision for the implementation support necessary post developing the toolkit, and Councils have no provision for implementation support in real dollar terms other than with in-kind staff.  Moving forward, implementation support should be identified and committed to if further real progress is to be achieved.  The risk is that all of the good work done to-date is undone because of a lack of investment in the implementation.

- The Joint Agencies continuing to commit to the project

- The three Councils collaborating on consenting and process issues, including the costs of consenting and financial/development contributions.

- Building  strong relationships with funding providers, in particular the Department of Building & Housing

## Conclusion

- Significant success has been achieved in facilitating housing development on Maori Land in the Western Bay of Plenty sub-region.  What has been achieved to-date requires investment if momentum is to be maintained and the potential that has been identified and partly unlocked is to be fully realised.